## Overview
Legend
Activity performed in month
Text | Example input: note - these are example inputs based on requirements in the Solar for All terms and conditions and are not meant to be exhaustive of steps applicants must take
Introduction:
This Excel Workbook is an optional example for applicants to fill in and submit for their Program Timeline.
Instructions:
For each tab, below is a description of the steps an applicant should complete to finish the template. Applicants should add and subtract rows as needed.
- Choose the tab for your program, SFA recipients should use either the 'May start' or 'September start' example tab, based on project start date, as identified on the SF-424
- Delete the extra timeline tab that does not align with your program period of performance
- In Cell B3, Identify which planning period type you will use: Full/Partial/None
- In Row 4, Update the # of months applicants will plan to use for the planning period
- In Row 7, Update the planning period to end earlier if you will be using less than 12 months
- In column B, Pre-Award and Conditional Drawdown Period Activities, add additional subheaders to organize as needed, and fill in activities the program will complete in the implementation period; add a row for each activity.
- In column B, Program Planning Activities, add additional subheaders to organize as needed, fill in activities the program will complete in the program planning period; add a row for each activity; an activity could be a discrete piece of analysis needed to refine plans/strategies detailed in the Program Narrative; a specific engagement with an important stakeholder; a process like a Request for Proposals or hiring a program manager; and any other type of activity which would be helpful to complete before launching the program.
- In column B, Implementation Period, add additional subheaders to organize as needed, and fill in activities the program will complete in the implementation period; add a row for each activity.
- In column C and D, Include the anticipated state and completion date for each activity
- In columns E through BL, indicate with a colored cell when the activity will occur; consider whether the activity is repeated on some frequency (e.g., a quarterly briefing); consider indicated clearly in the Financial Assistance Strategy workplan when the program will begin offering financial assistance to customers
-Please note that the list of reporting and compliance activities is not comprehensive and it is the responsibility of the grantee to understand all of its compliance and reporting requirements.

## SFA Timeline- May Start
Solar for All Program Timeline
Planning Period Type Used: [Full/Partial/None]
Planning Period: [12 Months]
Period of Performance: 5/01/2024- 4/30/2029
 | time axis 2024-05-01 to 2029-12-01
Activity Type |  |  | 2024-05-01: Pre-award and conditional drawdown period; 2025-01-01: Program Planning (12 Months); 2026-01-01: Implementation Period
|  |  | Period of Performance and Budget Year 1 | [11 empty] | Period of Performance and Budget Year 2 | [11 empty] | Period of Performance and Budget Year 3 | [11 empty] | Period of Performance and Budget Year 4 | [11 empty] | Period of Performance and Budget Year 5
Pre-Award and Conditional Drawdown Period Activities | Anticipated Start Date | Anticipated Completion Date | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Submit SFA detailed workplan and budget for approval within 90 days of award |  | Award date + 90 days | bar: Period of Performance and Budget Year 1 Month 3 to Period of Performance and Budget Year 1 Month 5
Activity 2
Program Planning Activities |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Draft QMP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 9 to Month 11
Draft QAPP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 9 to Month 11
[Maybe include] Submit additional subawards/PSCS to PO for approval | bar: Month 9 to Month 2
[Maybe include] Submit DBRA Labor and Equitable Workforce Development Plan | bar: Month 12 to Month 3
Activity 1 | bar: Month 9 to Month 10
Activity 2 | bar: Month 11 to Month 4
Activity 1 | bar: Month 9; Month 11; Month 1; Month 3; Month 5; Month 7
Activity 2 | bar: Month 9 to Month 12
Activity 1 | bar: Month 9 to Month 11
Activity 2 | bar: Month 12 to Month 2
[If construction included] Notify directly affected State, areawide, regional, and local entities of Financial Assistance for construction or land use planning pursuant to 40 CFR 29.7(b) to meet intergovernmental review requirement | 2025-03-01 | 2025-04-30 | bar: Month 11 to Month 12
Submit Revised Workplan and Budget at end of Planning Period |  | 2025-12-30 | bar: Month 8
Implementation Period |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Activity 1 | bar: Month 9 to Month 2
Activity 2 | bar: Month 12 to Month 3
Activity 1 | bar: Month 9 to Month 10
Activity 2 | bar: Month 11 to Month 4
Activity 1 | bar: Month 9; Month 11; Month 1; Month 3; Month 5; Month 7
Activity 2 | bar: Month 9 to Month 12
Activity 1 | bar: Month 9 to Month 11
Activity 2 | bar: Month 12 to Month 2
Activity 1 | bar: Month 9 to Month 8
Activity 2 | bar: Month 4 to Month 8
Reporting and Compliance Activities |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Draft QMP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 9 to Month 11
Draft QAPP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 9 to Month 11
MBE/WBE Reporting: EPA Form 5700-52A Annual Report Submitted (when the combined total of funds budgeted for procuring supplies, equipment, construction or services exceeds the Simplified Acquisition Threshold) |  | 10/30/2024, 10/30/2025, 10/30/2026, 10/30/2027, 10/30/2028, 10/30/2029 | bar: Month 6; Month 7; Month 6; Month 6; Month 6
Single Audit | bar: Month 6; Month 7; Month 6; Month 6; Month 6
Submit Interim Federal Finacial Report (SF425) annually |  | [Add date specific to program]
Submit Final Federal Financial Report | 2029-04-30 | 2029-08-28 | bar: Month 12
July 1-December 31 2024 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2024-12-31 | 2025-01-30
January 1-June 30 2025 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2025-06-30 | 2025-07-30 | bar: Month 3
July 1-December 31 2025 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2025-12-31 | 2026-01-30 | bar: Month 9
January 1-June 30 2026 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2026-06-30 | 2026-07-30 | bar: Month 2
July 1-December 31 2026 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2026-12-31 | 2027-01-30 | bar: Month 9
January 1-June 30 2027 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2027-06-30 | 2027-07-30 | bar: Month 3
July 1-December 31 2027 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2027-12-31 | 2028-01-30 | bar: Month 9
January 1-June 30 2028 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2028-06-30 | 2028-07-30 | bar: Month 3
July 1-December 31 2028 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2028-12-31 | 2029-01-30 | bar: Month 9
January 1-June 30 2029 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2029-06-30 | 2029-07-30
July 1-December 31 2029 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2029-12-31 | 2030-01-30
Post-closeout program strategy Submitted Prior to Program Closout |  | [prior to end of project period]
Final Report submitted | 2029-04-30 | 2029-08-28 | bar: Month 12
Closeout: January 1-June 30 2030 Semi-annual performance report submitted | 2030-06-30 | 2030-07-30
Closeout: July 1-December 31 2030 Semi-annual performance report submitted | 2030-12-31 | 2031-01-30
Closeout: January 1-June 30 2031 Semi-annual performance report submitted | 2031-06-30 | 2031-07-30
Closeout: July 1-December 31 2031 Semi-annual performance report submitted | 2031-12-31 | 2032-01-30
Review approved QMP annually |  | [Add date specific to program]
Review approved QAPP annually |  | [Add date specific to program]

## SFA Timeline- September Start (hidden)
Solar for All Program Timeline
Planning Period Type Used: [Full/Partial/None]
Planning Period: [12 Months]
Period of Performance: 9/01/2024- 8/31/2029 | time axis 2024-09-01 to 2029-12-01
Activity Type |  |  | 2024-09-01: Pre-award and conditional drawdown period; 2025-01-01: Program Planning (# Months); 2026-01-01: Project Deployment Period
|  |  | Period of Performance and Budget Year 1 | [11 empty] | Period of Performance and Budget Year 2 | [11 empty] | Period of Performance and Budget Year 3 | [11 empty] | Period of Performance and Budget Year 4 | [11 empty] | Period of Performance and Budget Year 5
Pre-Award and Conditional Drawdown Period Activities | Anticipated Start Date | Anticipated Completion Date | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Submit SFA detailed workplan and budget for approval within 90 days of award |  | Award date + 90 days
Activity 2
Program Planning Activities |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Draft QMP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Draft QAPP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Activity 1 | bar: Month 5 to Month 10
Activity 2 | bar: Month 8 to Month 11
Activity 1 | bar: Month 5 to Month 6
Activity 2 | bar: Month 7 to Month 12
Activity 1 | bar: Month 5; Month 7; Month 9; Month 11; Month 1; Month 3
Activity 2 | bar: Month 5 to Month 8
Activity 1 | bar: Month 5 to Month 7
Activity 2 | bar: Month 8 to Month 10
[If construction included] Notify directly affected State, areawide, regional, and local entities of Financial Assistance for construction or land use planning pursuant to 40 CFR 29.7(b) to meet intergovernmental review requirement | 2025-05-01 | 2025-06-30 | bar: Month 9 to Month 10
Submit Revised Workplan and Budget at end of Planning Period |  | 2025-12-30 | bar: Month 4
Project Deployment Period |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Activity 1 | bar: Month 5 to Month 10
Activity 2 | bar: Month 8 to Month 11
Activity 1 | bar: Month 5 to Month 6
Activity 2 | bar: Month 7 to Month 12
Activity 1 | bar: Month 5; Month 7; Month 9; Month 11; Month 1; Month 3
Activity 2 | bar: Month 5 to Month 8
Activity 1 | bar: Month 5 to Month 7
Activity 2 | bar: Month 8 to Month 10
Activity 1 | bar: Month 5 to Month 4
Activity 2 | bar: Month 12 to Month 4
Reporting |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Draft QMP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Draft QAPP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
MBE/WBE Reporting: EPA Form 5700-52A Annual Report Submitted (when the combined total of funds budgeted for procuring supplies, equipment, construction or services exceeds the Simplified Acquisition Threshold) |  | 10/30/2024, 10/30/2025, 10/30/2026, 10/30/2027, 10/30/2028, 10/30/2029 | bar: Month 2; Month 3; Month 2; Month 2; Month 2
Submit Interim Federal Finacial Report (SF425) annually |  | [Add date specific to program]
Submit Final Federal Financial Report | 2029-08-31 | 2029-12-29 | bar: Month 12
July 1-December 31 2024 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2024-12-31 | 2025-01-30 | bar: Month 5
January 1-June 30 2025 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2025-06-30 | 2025-07-30 | bar: Month 11
July 1-December 31 2025 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2025-12-31 | 2026-01-30 | bar: Month 5
January 1-June 30 2026 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2026-06-30 | 2026-07-30 | bar: Month 10
July 1-December 31 2026 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2026-12-31 | 2027-01-30 | bar: Month 5
January 1-June 30 2027 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2027-06-30 | 2027-07-30 | bar: Month 11
July 1-December 31 2027 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2027-12-31 | 2028-01-30 | bar: Month 5
January 1-June 30 2028 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2028-06-30 | 2028-07-30 | bar: Month 11
July 1-December 31 2028 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2028-12-31 | 2029-01-30 | bar: Month 5
January 1-June 30 2029 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2029-06-30 | 2029-07-30 | bar: Month 11
July 1-December 31 2029 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2029-12-31 | 2030-01-30
Post-closeout program strategy Submitted Prior to Program Closout |  | [prior to end of project period] | bar: Month 12
Final Report submitted | 2029-08-31 | 2029-12-29 | bar: Month 12
January 1-June 30 2030 Semi-annual performance report submitted | 2030-06-30 | 2030-07-30
July 1-December 31 2030 Semi-annual performance report submitted | 2030-12-31 | 2031-01-30
January 1-June 30 2031 Semi-annual performance report submitted | 2031-06-30 | 2031-07-30
July 1-December 31 2031 Semi-annual performance report submitted | 2031-12-31 | 2032-01-30
Review approved QMP annually |  | [Add date specific to program]
Review approved QAPP annually |  | [Add date specific to program]